## Sheet1
XXX School / Trust Risk Reduction Plan (date produced)
Key to risks: (L = Likelihood; F = Financial; R =Reputational)
Likelihood |  |  | Impact (financial/reputational)
1. extremely unlikely; rare occurrence |  |  | 1. not critical to continued operations
2. unlikely |  |  | 2. minor impact in limited areas
3. moderately unlikely |  |  | 3. minor impact in many areas
4. very likely, regular occurrence |  |  | 4. significant impact; would not affect continued operations in short term but might in long term
5. highly likely |  |  | 5. significant impact; in medium term; relates to substantial operational areas
6. extremely likely; frequent occurrence |  |  | 6. fundamental to continuing operations
For further guidance refer to the Risk Strategy document
Risk Reduction Plan Number | Risks | Early Warning Indicators (Existing Monitoring) | Mitigating Factors (Existing Controls and Actions) | Net Score [L] | Net Score [F&R] | Net Risk Score Total [(F&R) x L] | Action | Milestones with dates | Director / Head of School / Service Area | Line Manager | Progress update against milestones
Colindale | Failure to achieve LSC support for the Colindale AiP | Colindale scores poorly on LSC prioritisation criteria. Construction-ready projects absorb all available capital funds. | LSC prioritisation criteria - except Readiness - appear to favour Colindale. | 6 | 6 | 36 | Make Colindale 'prioritisation-ready' by progressing contracts with LBB and with co-dependent third party (Fairview New Homes). | 3 June meeting of LSC National Council. | Project Director: Colindale | Principal | Member of peer review group with 4 other colleges. Several successful bids for assistive technology.